## Slide 1: Cut-over Plan
2020. 06
S/4HANA Conversion Project TFT
CONFIDENTIAL
ERP, APO, BW

## Slide 2: Deploy Phase : D-50
Today, we have about 50 days left until Go-live, and we are in the deployment stage to perform BW, ERP, and APO Cut-over activity after the rehearsal test.
ERP Cut Over
APO Cut Over
BW Cut Over
Today

## Slide 3: Agenda
Performance plan
Performing method
  Cut-over Task
  Conference and communication
  R&R by business
Action plans for business partners
Go-live Decision

## Slide 4: Cut-over Plan
S/4HANA Cut-over is first performed in BW(7/13 - 7/19), and followed by ERP and APO in parallel (7/28 - 8/10). The overall schedule for Cut-over schedule is as follows
I. Performance plan
S/4HANA Cut-over Overview
‘20. 07. 06
‘20. 07. 13
‘20. 07. 20
‘20. 07. 27
’20. 08. 03
‘20. 08. 10
BW Cut-over (07/13 ~ 07/19)
ERP, APO Cut-over (07/28 ~ 08/10)
[SUM]Extraction
[SUM]Configuration
[SUM]Check
[SUM]Processing
Developing Object Lock
Request for ERP table backup
[SUM]Execution
Transfer operating system
Application conversion
Modify BW connected RFC
Modify EAI I/F
Check BI Jaba, BO, APO, PORTAL, FOUNDRY connection
Bex Reporting inspection
Process chain
Rescheduling
BW Go-live
(07/19 18:00)
07/06
07/28 – 08/07
07/20
07/19
07/31
Confirm plan order
Check logistics closing/completion
Check FI/CO closing/completion
Check completion of cost calculation
08/07 – 08/10
Stop batch and block user access
APO SUM (51h)
ERP SUM (50h)
FI/CO migration
Decide Go/Back
Freeze developing object
Designate authorization and menu
Oracle DB upgrade (11g  12g)
Final CTS apply
Unable to modify/reflect developing object
3rd CTS Synchronization (GSP  GE1)
08/10
Check EAI & Legacy service connection
Fiori service connection
Check BW connection
EAI and Batch re-operation
ERP/APO Go-live
(08/11 00:00)
BW-Uptime
BW-Downtime
BW-Post Act.
ERP/APO-Uptime
ERP/APO-Downtime
ERP/APO-Post Act.
07/13 – 07/17
07/17 – 07/19
07/19

## Slide 5: Cut-over Plan > ERP & APO
In particular,ERP, APO Cut-over which influences business downtime is divided into 4 stages :Preparation, Uptime, Downtime, and Post Activity, and is performed for about 13 days. (Excluding the preparation period). About 78 hours of downtime is estimated.
I. Performance plan
System Downtime 78 hours
Category | Preparation | Uptime | Downtime | Post Activity
 | ‘20. 07. 06 ~ 07. 31 | ‘20. 07. 28 ~ 08. 07 | ‘20. 08. 07 ~ 08. 10 | ‘20. 08. 10
Milestone |  |  |  | 
ERP |  |  |  | 
APO |  |  |  | 
Major procedure | Delete table for Downtime optimization (CBO/STD) Designate authorization and menu Upgrade Oracle DB (10g  12c) Upgrade SAP Component SI-Check 3rd CTS synchronization (GSP  GE1) Reflect final CTS (GSP, GE1) | SUM Uptime Delete Unused Planning Area Confirm plan order Close settlement for previous month Check FI/CO settlement/closing Check completion of real cost calculation Create/adjust price master creation and adjustment | Stop Batch Job and User Lock Stop EAI & Legacy System service Check CIF Model Intergration Active SUM Downtime Transfer Notes & CTS Check Object/source system CO migration and verification | Transfer developing program Program verification Data verification Check major functions of each module Verify EAI & Legacy system service connection Start process chain Connect Fiori Service Batch Job re-operation and Unlock User
Freeze Developing Object 07/06 (09:00)
Design-ate
authori-zation
&
menu
Oracle
DB
upgrade
3rd CTS synchronization
Reflect final CTS
ERP SUM
(Uptime)
APO SUM
(Uptime)
Stop ECC system
08/07 (18:00)
Check FI/CO settlement/completion
ERP SUM
(Down
time)
APO SUM
(Down
time)
FI/CO
Migration
Go-live Decision
8/10 (22:00)
Go-live
8/11 (00:00)
Verify EAI / Legacy connection &
All programs
Transfer Development program and authorization/ menu
EAI re-operation
Batch Job re-operation
Migrationpre-work
Transfer Notes

## Slide 6: Cut-over Major Activity > ERP & APO
I. Performance plan
Cut-over Task
Person in
charge
Schedule
Start freezing developing object (For managing system)
PMO
07/06 09:00 ~
Designate authorization and area menu (Transfer from GE1 to 8/10 CTS)
ALL
07/06 ~ 07/24
Delete tables for Downtime optmization(CBO/STD)
BC
07/13 ~ 07/27
Upgrade Oracle DB (11g  12c)
BC
07/19 00:00 ~ 04:00
Upgrade SAP Component (SAP_BASIS, SAP_BW)
BC
07/19 04:30 ~ 09:00
3rd CTS synchronization (GSP  GE1)
ALL
07/20 18:00 ~ 19:00
Execute SI-CHECK program
BC
07/23 ~ 07/24
Check total amount of depreciation for DISA / lease assets class Customizing
FI
07/25 09:00 ~ 18:00
Reflect final CTS (GSP, GE1)
ALL
07/31 14:00 ~ 15:30
Unable to modify/reflect developing object (Code freezing)
BC
07/31 16:00 ~
Major inspections
Preparation
Uptime
Downtime
Post-Act
Check Code Freezing notification
Check newly registered authorization (BP/MIGO..)
Table list for deletion (Type/Count)
-
-
List for 3rd CTS synchronization (Sample inspection)
SI-Check result list (Check the reflection)
-
List for 3rd CTS synchronization (Sample inspection)
-
Go-Live

## Slide 7: Cut-over Major Activity > ERP & APO
I. Performance plan
Cut-over Task
Person in
charge
Schedule
ERP SUM(Uptime)
07/28 ~ 08/07
[운영 적용] Delete unused Planning Area
07/24 17:00 ~ 18:00
Confirm plan order (PP/DS using plant)
07/27 ~ 08/05
APO SUM(Uptime)
07/29 ~ 08/07
Check Logistics closing/completion
~ 08/03 18:00
Check FI/CO , cost closing/completion
~ 08/07 18:00
Adjust Commitment Item Category
08/07 15:30 ~ 16:00
Create Cost Element
ALL
08/07 16:00 ~ 16:30
Major inspections
Preparation
Uptime
Downtime
Post-Act
BC
APO
APO
BC
SCM
FCM
CO
-
Check of 운영 work proceed
Check for remaining planning order
-
Check for closing by person in charge
Check for closing by person in charge
-
-
Go-Live

## Slide 8: Cut-over Major Activity > ERP & APO
I. Performance plan
Stop ECC system, stop Batch Job and block users (Deactivate DOOINS accessing menu)
08/07 18:00 ~ 19:00
Stop EAI & Legacy System service
08/07 18:00 ~ 19:10
APO SUM(Downtime) start ~ end
08/07 18:00 ~ 08/09 21:00
ERP SUM(Downtime) start ~ end
08/07 18:00 ~ 08/09 20 :00
Preparation
Uptime
Downtime
Post-Act
BC
Legacy
BC
BC
Check if managing system stopped
-
-
-
Pre-works for FI/CO Migration
08/09 20:00 ~ 21:00
FI, CO
-
Fi/CO Migration start ~ end
08/09 21:00 ~ 08/10 15:00
PMO
-
Check CIF Model Integration Active
08/09 20:00 ~ 20:30
CIF Variant version upgrade
08/09 20:30 ~ 21:00
CCR Delta Report Connection
08/09 20:00 ~ 21:00
APO
APO
APO
Check of Activation (T-Code : CFM2)
Check of Variant appliance(T-Code : CFM1)
Check of execution (Execute the program)
Go-Live
Cut-over Task
Person in
charge
Schedule
Major inspections

## Slide 9: Cut-over Major Activity > ERP & APO
I. Performance plan
Preparation
Uptime
Downtime
Post-Act
Apply ERP related CTS (GE1  GSP)
ALL
08/10 15:00 ~ 17:00
ECC vs S/4HANA Data verification
ALL
08/10 18:00 ~ 20:00
Check authorization and menu
ALL
08/10 17:00 ~ 18:00
Send BW related CTS (GE1  GSP)
BC
08/10 18:00 ~ 18:30
-
Check for data check list
-
Check for changes in ERP
DMS setting: Add DC30 extension and release authorization group
BC
08/10 19:00 ~ 22:00
MASTERSAF Import
BC
08/10 19:00 ~ 22:00
-
-
Encryption (SPIN) Import
BC
08/10 19:00 ~ 22:00
Reboot Batch Job
BC
08/10 20:00 ~ 22:00
Check for encryption table inquiry
Check Batch Job List
Check for S/4HANA connection settings(S/4HANA <-> BW)
BW
08/10 19:00 ~ 19:30
BW - CTS transfer(BPD  BPP)
BW
08/10 19:30 ~ 20:00
-
Check for changes in BW
Go-Live
Cut-over Task
Person in
charge
Schedule
Major inspections

## Slide 10: Cut-over Major Activity > ERP & APO
I. Performance plan
Preparation
Uptime
Downtime
Post-Act
Take action on Pegging Area error(특성 재 CIF)
APO
08/10 16:00 ~ 17:00
Check by specific class table inquiry
Check major functions of each module and process manual
APO
08/10 21:00 ~ 21:30
Check list of each module inspection
S/4HANA Conversion Go/Back decision
PMO
08/10 22:00 ~
Check the final list of system conversion inspection
Verify EAI & Legacy System service connection
Legacy
08/10 18:00 ~ 20:00
Check for system connection list
Activate SAP accessing menu of DOOINS portal
Legacy
08/10 18:00 ~ 19:00
Check for system connection
Connect EAI S/4 HANA
EAI
08/10 18:00 ~ 20:00
List of inspection for each EAI system(Inquiry screen)
Interface test with DOOINS,SSO,EP
BC
08/10 19:00 ~ 20:00
Check system connection
Fiori - Front system interface: 운영(GSP)
BC
08/10 18:00 ~ 19:00
Check if Fiori works well (Check screen)
Check of legacy system connection
Legacy
08/10 20:00 ~ 22:00
Check major functions of each module
ALL
08/10 19:00 ~ 22:00
Check list of Legacy & 3RD Party
Check system checklist
Go-Live
Cut-over Task
Person in
charge
Schedule
Major inspections

## Slide 11: Cut-over Major Activity > ERP & APO
I. Performance plan
Preparation
Uptime
Downtime
Post-Act
Execute Transaction CCR
APO
08/10 22:00 ~ 08/11 02:00
Check the error after the execution and take action
S/4HANA Go-live
PMO
08/11 00:00
System open notification
Recreate plan order
APO
Re-execute MRP
APO
08/11 02:00 ~ 05:00
08/11 05:00 ~ 06:00
Go-Live
Cut-over Task
Person in
charge
Schedule
Major inspections
Check the error after the execution and take action
Check the error after the execution and take action

## Slide 12: Cut-over Plan > Code Freezing & Downtime
32 hours of BW, and 78 hours of ERP/APO system downtime is necessary for S/4HANA conversion cut-over activity.
I. Performance plan
System Downtime Period
BW | Korea | UTC+9 | 2020/07/17 (Fri) 19:00 | ~ | 2020/07/19 (Sun) 01:00 | Go-live (7/19, 18:00)
ERP / APO | Korea | UTC+9 | 2020/08/07 (Fri) (18:00) | ~ | 2020/08/11 (Tues) 00:00 | Go-live (8/11, 00:00)
 | China | UTC+8 | 2020/08/07 (Fri) (17:00) | ~ | 2020/08/10 (Mon) 23:00 | 
 | Europe | UTC+2 | 2020/08/07 (Fri) (11:00) | ~ | 2020/08/10 (Mon) 17:00 | 
 | North America | UTC-4 | 2020/08/07 (Fri) (05:00) | ~ | 2020/08/10 (Mon) 11:00 | 
 | South America | UTC-3 | 2020/08/07 (Fri) (06:00) | ~ | 2020/08/10 (Mon) 12:00 | 
(Downtime is based on local time)
System
Corp.
Time-zone
Remark
System Downtime
Code Freezing Period
ECC /APO | Korea | UTC+9 | 7/6 (Thurs) | 09:00 | Start freezing developing object | Allow immediate modification of closings and legal issues
 |  |  | 7/31 (Fri) | 16:00 | Lock developing object | Unable to develop/transfer ABAP or CTS
System
Corp.
Time-zone
Details
Remark
Applying date

## Slide 13: [Backup] Downtime Task > ECC & APO
Cut-over in ERP and APO areas are performed in parallel from 8/7 to 8/10 and the following are the key actions and schedules for each system within the Downtime period (78 hours).
I. Performance plan
8/7(Fri)
8/8(Sat)
8/9(Sun)
8/10(Mon)
18 o’clock
21 o’clock
13 o’clock
15 o’clock
24 o’clock
HANA
ECC
BW
Legacy
APO
20 o’clock
1)SUM : Software Update Manager
Downtime 78시간
Check closing of previous month
Load BW Delta
Data
SUM1) execution (50 hours)
Transfer
Notes
Inspection and performance of
Accounting migration (18 hours)
Transfer
developing
program
All program
verification
(SAP,EAI etc.)
Compare migration data
Compare
migration
data
Migration
Follow-ups (9 hours)
Block
groupware menu
Legacy restoration
And inspection
Reserve Batch Job
Batch Job
re-operation
Stop
Batch Job
Stop process chain
ECC Vs S/4HANA
compare
EAI re-operation
SUM execution preparation
영역별 SPDD 내역 반영
Groupware menu
restoration
Change
CIF connection
Stop CIF connection
CIF
test
SUM execution preparation
Install
Live Cache
Live Cache
Download
Live Cache Upload
Check activation and allocation of Logical System, Integration Model
Start process chain
/Take actions
SUM1) execution
M/G
DATA verification
Transfer
CTS
Inspect
Object/
source system
BW
ERP Setting
BW
Data extraction
S/4HANA Open
APO & ERP Cut Over Plan
22 o’clock
Go/Back
Decision

## Slide 14: [Backup] Downtime Task > BW
BW Area Cut-over is performed from 7/17 to 7/19. Key actions and schedules within the Downtime period (47 hours) are as follows.
I. Performance plan
7.19(Sun)
Stop process chain
7/17(Fri)
7/18(Sat)
7/20(Mon)
House Keeping 사전완료
Data verification data preparation complete
CTS transfer
Check monitoring
HANA DB backup
1)SUM : Software Update Manager
01:00 am
19 o’clock
20 o’clock
03:00 am
07 pm
12 o’clock
16 o’clock
09:00 pm
06:00 pm
Downtime 47 hours
BW backup
11:00 pm
SUM execution (30 hours)
SUM1) Pre-work
RFC modification (ERP, APO)
04:00 pm
SUM Follow-ups(17 hours)
BW Go-live
BW
Object and source system inspection
Bex. BQ
test
1st
Data
verifica-tion
EAI I/F test
Batch restart
Start process chain
BW on HANA Cut Over Plan

## Slide 15: Cut-over Detailed Activity and Check List
Cut-over activity is shared with PMOs and staff members by checking progress by item and time, and in case of major activities, a separate check list is utilized to ensure that there is no missing task when performing Cut-over.
II. Performing method
Cut-over Activity (ERP/APO)
Selective
Record the actual performance time
and progress by activity
Check List by each major activity
(Separately managed)

## Slide 16: Meetings and Communications
Regular Conference Call
There is no structured reporting for each task in order to focus on the Cut-over during the ERP and APO downtime period. However, regular meetings are held to monitor Cut-over progress, Next progress, and issues.
II. Performing method
Communication plan
Participants: PMO, Key persons in each area (Consultants, 3rd Party, etc. )
Key issues : Complete in activity unit, Process next, Share issues and risks
Method: MS Teams meeting
Schedule:
Report for finishing Activity and Task
Targets: PMO, Key persons in each area (Consultants, 3rd Party etc), Team members
Details: Report completion by Activity units, Share issues and risks
By : e-mail
Schedule: Occasional (Before/after performing major activity or task)
Share the completion of major activities
Report issues/risks
PMO
Key persons
in each area
Team members
Share the status of major activities
Request for additional work if necessary
Instruct work in Task units
Share work status
Report completion by Task units
Report Issues/risks
Meetings
Steps |  |  | 
Period | 7/28 ~ 8/7 | 8/7 ~ 8/10 | 8/10 ~ 8/17
Cycle | (If necessary) | Once a day | Once a day
Time | (TBD) | 21:00 (KST) | 21:00 (KST)
After Go-live
Downtime
Before Downtime
※ PMO leads the communication of foreign corporations and merges the Cut-over results.

## Slide 17: R&R by business
To ensure smooth communication and prompt action during Cut-over, especially during Downtime, the PMO and key persons in each area are always on standby to monitor progress and not affect the Go-live schedule.
II. Performing method
R&R |  | Targets | 8/7 | 8/8 | 8/9 | 8/10
PMO | Cut-over monitoring and communications Make Decisions for important issues Confirm the final result of cutover | Kim Heeyoung, Kim Sangwook, Lee Bumsuk, Chong Jooyoung, Oh Jiyeon, Kim Jaewon | S | S | S | M
ERP | Preparation for conversion and SI-Check inspection Post activity and subsequent migration for each module Verification of each module’s functions and data | FITR: Choi Mihyeon CO: Kim Eunju PP: Park Jihong SD: Hwang Inseok, Park Minjeong MM: Lim Byungki (*Support of DDI operators) | S | M | M | M
APO | Inspect major functions for each APO module Perform Process Chain manual Inspect LiveCache | Park Keunsoo | M | S | M | S
BC | Execute SUM (ERP, APO) Install AP System Setup and verification (DMS setting etc.) | Lee Jaeyoon, Park Jinwoo | M | M | M | M
Legacy | Verify EAI & Legacy system connection Inspect Local system function (Tavant, GRC etc.) | China: Jang Yeongjin Korea: Son Yeongcheol America: Prashanth / Brian Brazil: Marcelo | M | S | S | M
(M: Main, S: Support / Detailed work plans for each workforce will be posted separately)

## Slide 18: [Backup] Phone numbers of the person in charge
II. Performing method
Area |  | Name | E-mail | Phone number
PMO |  | Kim Heeyoung | heeyoung.kim@doosan.com | 010-4631-1735
 |  | Kim Sangwook | sangwook1.kim@doosan.com | 010-5307-9428
 |  | Lee Bumsuk | bumsuk.lee@doosan.com | 010-2788-4939
 |  | Chong Jooyoung | jooyoung.chong@doosan.com | 010-6201-4689
 |  | Oh Jiyeon | jiyeon.oh@doosan.com | 010-8412-0574
ERP | FITR | Chang Sukhee | sukhee.chang@doosan.com | 010-6260-7463
 |  | Choi Mihyun | mihyun1.choi@doosan.com | 010-7108-5360
 | CO | Kim Jooil | jooil.kim@doosan.com | 010-5717-6739
 |  | Kim Eunju | eunju1.kim@doosan.com | 010-8959-7554
 | SD | Hwang Inseok | inseok1.hwang@doosan.com | 010-3211-2234
 |  | Park Minjung | min-jung.park@doosan.com | 010-9046-2567
 | MM | Lim Byungki | byungki.lim@doosan.com | 010-3226-0217
 | PP | Park Jihong | jihong2.park@doosan.com | 010-5247-9012
APO |  | Park Keunsoo | keunsoo2.park@doosan.com | 010-9014-8083
BC |  | Lee Jaeyun | jaeyun.lee@doosan.com | 010-8631-7058
 |  | Park Jinwoo | jinwoo2.park@doosan.com | 010-5266-5226
Legacy | KO | Son Youngchul | youngchul.son@doosan.com | 010-9460-3729
 | CH | Zhang Yongzhen | yongzhen.zhang@doosan.com | -
 | NA | Prashanth Vayilla | prashanth.vayilla@doosan.com | -
 |  | Brian Grellinger | brian.grellinger@doosan.com | -
 | SA | Marcelo Bruno | marcelo.bruno@doosan.com | -

## Slide 19: Action Plans for business partners
Notifications and requirements for business partners to prepare for the cut-over and system downtime
III. Action Plans for business partners
Major Action Plans of each area
- Request to the PI team to fill in
Category
Detailed Action Item
Schedule(Due)
Area
Performer
FI | July closing | Clear the differences between the total account ledger, and bond and debt ledger Clear the negative stock, difference between stock and inventory, and 선매출 Establish a plan to clean up the amount of inventory that is not related to the cost receipts and disbursements | 8/7 | 
 | TBU | Secure the service parts beforehand |  | 
 |  | Pre-notification to the dealers |  | 
APO | Planning order arrangement | Confirm/Complete by Planning order -> Production order | 8/7 | 

## Slide 20: Go-live final inspection and decision
The implementation of Go-live is based on the results of the Go-live Checklist by predefined Function, Data, Interface, and CTS, and a final inspection meeting is held at 22:00 before the Go-live.
IV. Go-live Decision
Based on Go-live 1)
Final Go-live Inspection meeting
Date
And
Place
8/10 (Mon) 22:00 – After the finance migration, transfer post activity
FASTFIVE meeting room(TBD) or online
Attendees
PMO & PI
Person in charge of BC
Person in charge of each module
Agenda
Check inspection results for Go-Live and any further issues
  Result of BC’s System Copy and Post Job work result (Appliance of final transferred CTS etc.)
  Result of each module’s CTS application and the interface inspection
※ At that point, when the final decision cannot be made,
Before Go-live, check the possibility of final action
Proceed Go-live or Contingency Plan
Check CTS application
Check the test performance of the display screens after applying the final development server CTS.
In case of major registration/modification program, proceed transfer source eye check (Based on recent changes).
System Interface
Check the succession of I/F with the Legacy & 3RD Party solution (Display Only)
Check any abnormalities of major systems such as EAI, EDI, EP,APO, BW, and SSO.
Data Verification
There is no problem with key data verification results by module compared to existing ECC. (Data count & Report verification)
Downtime goal
Complete Go-live within 72 hours of downtime
1) Go/Back decision Check list is managed in the separate Excel file

## Slide 21: Contingency Plan
S/4HANA
If the Go-live inspection results in severe Downtime delays or Critical problems that cannot be immediately taken, Contingency Plan is activated to rollback to the ECC.
IV. Go-live Decision
Suji DC
Backup
As-Is operating system
ECC/APO/BW
Rollback (Case 2, Case 3)
To-Be operating system
Go-live
Go (Case 1)
AWS
Go (Case 2, Case 3)
Result of Go-live Decision
Result of final review |  | Decision
Case 1 | No system abnormality No error in the data or function | Open
Case 2 | System Downtime Delay (Check the time required by section) | Review on the final downtime and decide
Case 3 | Critical issue occurrence (Data, Function, I/F, etc.) | Determine if immediate action is possible
Contingency Plan (Rollback)
Required time
  Within 2 hours after the decision (There is no changes in the ECC, so it can be quickly restored by backup)
Rollback
  System: ERP, APO, BW, Legacy system
  I/F: EAI, RFC etc.
Check list of normal completion
  I/F verification of functions and systems
  Data verification
System
Operation
Stopped
Downtime
conversion
Infra inspection
and
final inspection
Go/Back
Go (Case 1)

## Slide 22
End of Document